## EXAMPLE – Agile Epic Req
Agile Epic Requirements Template – Example
1. Epic Overview
EPIC NAME
Real-Time EV Charging Station Monitoring
EPIC OWNER |  | EPIC ID | CREATION DATE | LAST UPDATED
Alexandra |  | PC-EPIC-001 | 07/22/20XX | 07/22/20XX
2. Epic Description
SUMMARY
Implement a real-time monitoring system for EV-charging stations to provide instant status updates and alerts.
DETAILS
This epic involves developing a robust monitoring solution that integrates with all charging stations, enabling real-time data collection and analysis. The system will display station availability, charging status, and performance metrics on a centralized dashboard.
GOALS (STORIES) – Functional Requirements
– Enhance operational efficiency by providing up-to-date station status. – Improve user satisfaction with real-time availability updates. – Enable proactive maintenance by identifying potential issues early.
3. Business Case (Non-Functional Requirements)
VALUE PROPOSITION
The real-time monitoring system will increase the efficiency and reliability of our EV-charging network, leading to higher customer satisfaction and reduced downtime.
SUCCESS CRITERIA
– Achieve 95% accuracy in real-time status updates. – Reduce downtime by 20%. – Receive positive feedback from at least 80% of users in post-implementation surveys.
4. Acceptance Criteria
CONDITIONS OF SATISFACTION
– The dashboard must display real-time status updates with less than a five-second delay. – The system must send alerts for any significant status changes or issues.
DEFINITION OF DONE (DoD)
– Code is reviewed and approved. – All unit and integration tests are passed. – User documentation is updated. – Stakeholder approval is obtained.
6. User Stories and Tasks
User Story ID | Story Name
PC-US-001 | Receive Status Alerts
User Story Description
As a maintenance team member, I want to receive alerts when a station goes offline so that I can address issues promptly.
Acceptance Criteria
The system must send alerts within one minute of a status change.
TASKS
Task ID | Task Name |  | Description
PC1-TASK-001 | Develop Real-Time API Integration |  | Create an API to collect real-time data from charging stations.
PC1-TASK-002 | Build Monitoring Dashboard |  | Develop a user interface to display real-time data.
PC1-TASK-003 | Implement Alert System |  | Create a system to send alerts based on predefined conditions.
PC1-TASK-004 | Conduct User Testing |  | Perform testing with a select group of users to gather feedback and identify issues.
User Story ID | Story Name
PC-US-002 | View Charging Station Status
User Story Description
As a user, I want to view the current status of charging stations in real time so that I can find an available station quickly.
Acceptance Criteria
The dashboard must show the real-time status of each station.
TASKS
Task ID | Task Name |  | Description
PC2-TASK-001 | Develop Real-Time Data Integration |  | Integrate APIs/sensors to fetch live charging station availability data.
PC2-TASK-002 | Design Charging Station Dashboard |  | Create a UI displaying station locations, availability, and charging speed.
PC2-TASK-003 | Implement Status Refresh Mechanism |  | Ensure the dashboard auto-refreshes every 30 seconds for real-time updates.
User Story ID | Story Name
PC-US-003 | identifying potential issues early.
User Story Description
As a user, I want to identiify the potential issues that would ruin my car before they actually happen.
Acceptance Criteria
There should be pop-up windows when potential issues are detected.
TASKS
Task ID | Task Name |  | Description
PC3-TASK-001 | Develop Issue Detection Algorithm |  | Build a system to analyze vehicle diagnostics
PC3-TASK-002 | Design Alert Notification System |  | Create pop-up alerts with issue details
PC3-TASK-003 | Integrate Predictive Maintenance |  | Link diagnostics to a database of common failure patterns for early warnings.
6. Timeline | Thursday, August 1, 20XX |  | Monday, September 30, 20XX
MILESTONE |  |  | DATE OF MILESTONE
API Integration Complete |  |  | Thursday, August 15, 20XX
Dashboard Development Complete |  |  | Monday, September 2, 20XX
User Testing Complete |  |  | Friday, September 20, 20XX
Final Review and Sign-Off |  |  | Monday, September 30, 20XX
7. Stakeholders
– Project Manager: Everett – Product Owner: Brooklyn – Development Team Lead: Henry – UAT Lead: Romy
8. Risks and Assumptions
RISKS | MITIGATION PLANS |  | ASSUMPTIONS
Potential delays in data integration from charging stations may occur. | Hold regular status meetings to monitor progress and address issues promptly. |  | All charging stations are capable of providing real-time data.
Unforeseen technical challenges in real-time data processing may arise. | Allocate additional resources for data integration tasks. |  | Required APIs are available and functional.
9. Resources
TEAM MEMBERS
NAME |  | TITLE
Henry |  | Development Team Lead
Jason |  | Backend Developer
Makara |  | Frontend Developer
Sasha |  | QA Engineer
TOOLS AND TECHNOLOGY
– API Gateway – Real-Time Data Processing Framework – Web Dashboard Framework
10. Progress Tracking |  |  | STATUS
In Progress
PROGRESS UPDATES
API integration development started on August 1, 20XX.
Initial dashboard design completed on August 10, 20XX.
11. Comments and Notes
Any additional notes or comments related to the epic can be added here for reference.

## BLANK – Agile Epic Req
Agile Epic Requirements Template
1. Epic Overview
EPIC NAME
Mobile App for Online Laptop Retailer
EPIC OWNER |  | EPIC ID | CREATION DATE | LAST UPDATED
Lebron James |  | PC-EPIC-001 | 03/11/2025 | 03/13/2025
2. Epic Description
SUMMARY
Develop a new mobile app to complement an online laptop retailer.
DETAILS
The app will include an Augmented Reality (AR) feature to let customers visualize different laptop configurations, a chatbot for automated customer support, and a loyalty rewards system that provides returning customers with personalized discounts. Once all features are developed and tested, the app will be launched.
GOALS
– Implement AR functionality to allow customers to explore various laptop configurations. – Develop an AI-powered chatbot to improve customer support. – Create a loyalty program that offers exclusive deals to repeat customers.
3. Business Case
VALUE PROPOSITION
Improve customer engagement through AR-based visualization. Enhance customer service by reducing wait times with a chatbot. Boost customer retention with personalized loyalty discounts.
SUCCESS CRITERIA
–Achieve a 4.2-star rating on app stores within the first 2 months of launch. – Increase mobile sales by 15% within 6 months of launch. – Reduce customer support queries by 10% through chatbot functionality.
DEPENDENCIES
Third-Party Services: The app may require third-party services for payment processing, push notifications, and analytics.
4. Acceptance Criteria
CONDITIONS OF SATISFACTION
The AR feature must support at least 5 different laptop models. The chatbot should respond to queries within 10 seconds. The app must automatically send discount codes based on purchase history.
DEFINITION OF DONE (DoD)
– All code reviews are approved. – All unit and integration tests are passed. – User documentation is updated. – Stakeholder approval is obtained.
5. User Stories and Tasks
USER STORIES
User Story ID | Story Name
PC-US-001 | Augmented Reality Laptop Configuration
User Story Description
As a customer, I want to use augmented reality to visualize different laptop configurations so that I can make an informed purchase decision.
Acceptance Criteria
The AR feature should support at least 5 different laptop models, allowing users to customize storage, RAM, and color.
User Story ID | Story Name
PC-US-002 | AI Chatbot for Customer Assistance
User Story Description
As a customer, I want to chat with an AI assistant to get quick answers to my questions, so I don’t have to wait for live support.
Acceptance Criteria
The chatbot should respond within 10 seconds and handle at least 80% of common queries.
TASKS
Task ID | Task Name |  | Description
PC1-TASK-001 | Develop Augmented Reality Feature |  | Implement AR capabilities that allow customers to view and interact with 3D laptop models.
PC1-TASK-002 | Integrate AI Chatbot |  | Develop and integrate a chatbot to handle customer queries.
PC1-TASK-003 | Loyalty Discount System |  | Create a system that generates and sends exclusive discounts to repeat customers.
PC1-TASK-004 | Conduct User Testing |  | Perform testing with selected users to gather feedback and identify potential issues before launch.
6. Timeline | CREATION DATE |  | CREATION DATE
| Tuesday, March 11, 2025 |  | Tuesday, March 18, 2025
MILESTONE |  |  | DATE OF MILESTONE
AR Feature Development Complete |  |  | Tuesday, March 11, 2025
AI Chatbot Integration Complete |  |  | Thursday, March 13, 2025
Loyalty Discount System Complete |  |  | Sunday, March 16, 2025
Final Review & Approval |  |  | Tuesday, March 18, 2025
7. Stakeholders
Project Manager: Lebron James Product Owner: Michael Jordan Development Team Lead: David Tao UAT Lead: Jay Chou
8. Risks and Assumptions
RISKS | MITIGATION PLANS |  | ASSUMPTIONS
Technical challenges may slow development. | Offer additional resources and conduct regular technical reviews. |  | Customers will use devices that support AR.
The chatbot may struggle with complex queries. | Ensure seamless fallback to human support when needed. |  | The chatbot will be trained on a sufficient dataset to handle common queries.
9. Resources
TEAM MEMBERS
NAME |  | TITLE
David Tao |  | Development Team Lead
Lebron James |  | Project Manager
Jay Chou |  | UAT Lead
Michael Jordan |  | Project Manager
TOOLS AND TECHNOLOGY
AR Development Framework Chatbot Platform Mobile App Development Framework
10. Progress Tracking |  |  | STATUS
In Progress
PROGRESS UPDATES
AR development started on 03/11/2025.
Initial chatbot design completed on 03/12/2025.
11. Comments and Notes
The AR feature will be released for iOS first, with Android support coming later.